# Volunteer Coordination Steering Committee Meeting Notes

March 25, 2025

9:30-10:50 am

## Attendees:

- Jackie Golz

- Cristina Clark

- Jackie Miller

- Brooke Campbell

- Gary Flaharty

- Robert Nnake

## Past Meeting Minutes:

- Aiming to build everything by April

- Test the program in May

- Report out and then change focus to sustaining an improving

- Should all meetings be in person?

- Workgroup, yes

## Committee Updates:

- Recruiting

  - Reiterating that the ultimate goal in reaching out to companies is to get them to commit to volunteering during a disaster situation

  - Can you clarify how the VOADs tie in with the asks we are making to companies?

    - We will be building up the capacity for VOADs to receive and work with unsolicited volunteers

    - We will be discussing how to ensure that we do not neglect certain areas that historically have had less volunteer assistance

- Portal

  - We need to make sure that the OEMs know where to push people who are truly unsolicited volunteers

  - Existing 9-10 calls with VOADs

  - Have identified high-vulnerability zip codes

    - VOADs will look for groups that could be stationed in those areas

    - The group will then discuss these areas with the cities and the County

    - Set up a relationship between an area and a “geo job” (Kingwood - Muck and Gut)

  - Commitments: VOADs will always have an area that they are committed to serving

  - Mission Field: places that people are committed to outside of their residence

  - Community: places that people volunteer at that they don’t have a previous commitment to and would likely only volunteer there after ensuring their other commitments are in safe conditions

  - Since each page (Volunteer Kingwood, Volunteer Channelview, etc.) can be used, we can share opportunities widely

    - When volunteers click “respond” they will input their name, phone number, and email

      - What else do we need?

      - Once volunteers submit, they get an email thanking them and letting them know the contact information of the group they are volunteering with and any other relevant information

      - Ideally, a staff member would get on the phone with volunteers shortly after they’ve signed up to provide additional information as needed

  - About 12 job descriptions have been written

  - Gary will organize a demonstration of Volunteer Houston with Samir

  - If there is a job that is listed that requires a background check, how will the portal facilitate this?

    - The job descriptions include requirements for background checks for relevant positions (shelters, etc)

    - If a VOAD uses Sterling Volunteers to do their background checks, they can sync their background checks with Volunteer Houston

    - Different organizations may require different types of background checks

    - People will likely self-select the volunteer opportunities that don’t require a background check if they suspect they may not pass

    - Should communicate to organizations that they should only use background checks if there is a legitimate reason

    - CERT teams only use background checks in specific situations

  - Anything posted to Volunteer Houston will automatically be posted to Volunteer TX

- Volunteer Experience

  - Should we be thinking of group organizations’ volunteer experience?

    - If we are able to get a liaison ahead of time, they can shape their experience

    - Developing a resource would be helpful, but the conversation need not center on that resource

- Capacity Building

  - Gary’s action item is to talk to all OEMs and VOADs in April

  - Group has spoken to Houston Responds and Gulf Coast Disaster Readiness

    - Developing a master asset list through the VOADs

    - Have confirmed a gym, a kitchen, a parking lot to be able to accommodate volunteers

    - Will work to get more facilities with showers, sleeping areas, etc.

## General Notes:

- Last meeting we discussed developing a repository for the group

  - Will ask Angela for support on this

  - Gary can put documents on the VOAD website that will be password protected

- Recording volunteer hours for reimbursements

  - It’s important to record hours that are for city/County efforts

## Action Items:

- For Tuesday meeting: Presenting 1-3 slides for 15 minutes per group

- Meeting scheduled for 3/25 to be rescheduled for 4/2 and will be held in person at United Way