# Volunteer Coordination Steering Committee Meeting Notes

March 4, 2025

9:30-11:00 am

Meeting Goals:

- Battle Rhythm

- Monthly cadence

  - Meeting at the end of March, April, and May

- Charters of each group

  - What is missing from each of these groups?

- Coverage from SteerComm members in each committee

# 4 Committees:

- Recruiting

- Portal

- Volunteer Experience

- Capacity Building

# General Notes

- Mark Sloan and Jackie Miller met. Mark shared his expectations for Interfaith Ministries.

  - Need to streamline the communications between Harris County and COH OEM leadership and the rest of the staff, particularly because Stephanie is leaving.

  - Jackie Miller will also be working on the large group.

  - Christina Clark may be taking Stephanie’s spot on the SteerComm

- Jackie Miller may be joining the SteerComm

- Pods: OEM is in charge, but the pods will be run through Houston Public Works. A city representative will be in charge of the pods to ensure that there will be site managers/captains to receive volunteers, whether they are volunteers that had already committed or USVs

- Part of this process depends on getting job descriptions written

- Could pods also train a cadre of lieutenants that will be able to assist in receiving and assigning volunteers?

  - This ties into the Recruitment side: presents an opportunity for committed volunteers to meet an “immediate need”

- How would meeting locations be set up? How would this be related to the existing sites from the city (multi-service centers) and how would pods determine these locations?

  - There could be a pre-vetted list of locations to act as satellite locations

    - Non-profits can also provide this function

  - These could be set by census tract or zip code

  - The expectations for the pods is mostly to give a structure to the volunteer coordination through the use of captains and lieutenants

    - Piloting this through COH could give us a model to use for the County

  - Pods that are set up through the County or COH are easier to manage than efforts led by elected officials’ offices

    - We should limit duplication of efforts

    - Can elected officials be brought in in a small capacity?

    - Elected officials will partner with churches, neighborhood centers, etc. to establish a pod in addition to the ones that COH or the county open

      - These existing partnerships can be utilized to expand the overall group’s capacity to coordinate volunteers

    - Elected officials will use the human resources at churches/outside partners that allows them to tap into an existing group of people and limit their liability, and allows them to use their partner’s existing relationships to resource non-governmental resources ex. Sysco providing food donations

  - COH City Council set up tool banks, which allows Council members to use their own budgets to buy tools that are at their disposal to use in a disaster setting

    - Example: District B bought chainsaws, and they are working to train people to use them

    - Building grassroots capability

    - Can this be replicated?

      - This also has Council Members buy-in

      - This initiative makes them feel invested

      - Even if Council Members lead their own efforts, they can use our standardized model

    - This would fall under Committee #4

    - COH Legal does not want DON volunteers to be on private property with heavy machinery because of liability concerns

      - Leading training and facilitating trainings could subject COH and the County to liability

        - Can promote non-profits doing this work, but cannot be directly leading the work

  - Do we have a repository to keep our notes and drafts together?

    - Tommy will be exploring options to set this up

    - COH does not allow access to Google Suite

  - In regards to volunteer experience, in activation mode, volunteers should receive training in a location close to the place where they would be volunteering.

    - This would entail setting up multiple volunteer reception centers

    - The volunteer reception centers should not be set up in the same places as operating shelters

# Committee #1 Recruitment

- Taking a summary of what the plan is to be able to bring to employers and potential partners

- Formalize process for soliciting feedback from partners

- Currently, identifying large employers, agencies, to share

- Set expectations

- Make a presentation

- Tracking the number of volunteers they commit

- Can also consider having an MOU to make plans more concrete

- Once everything is put together, the plan should be presented to the partnership

- UnitedWay now has a Corporate Relations staff member

- Ideal plan is to ask a representative of the corporations to commit volunteers, and have them handle the recruitment of their volunteers

  - Should not be an obligation because of liability but because their employees may also be impacted.

  - Can give exact language for them to share with their employees

# Committee #2 Portal

- Gary, Samir are meeting to develop this on 3/5

- Will get a list of Volunteer Houston’s capability

- What is the user experience like?

- Can we get them sorted through appropriate filtering?

- Customizable Disaster Page

- To add: Check-in/Check-out process

- Clean, friendly, efficient

- Timeline to be updated tomorrow

- Will be important to understand the agencies’ responsibilities for this module

- It would be helpful to identify which positions will be inundated in the immediate when a disaster happens and which personnel group could handle with this volume of interfacing with volunteers

- Do needs posts need to be posted in blue sky?

  - Yes

  - This will give Samir time to approve all the needs posts

  - How quickly can these be posted?

  - Do we have a backup to Samir?

# Committee #3 Volunteer Experience

- Plan moving forward is to develop the playbook that can be handed to any volunteer leader (electeds, non-profits, churches, etc) so they can be prepared to handle an emergency

  - More tactical in nature so any volunteer leader can pick it up and use it

  - Would this be helpful? What content would be included?

- Houston Public Works (HPW) and Department of Neighborhoods (DON) will both work on pods, and DON will be training their staff to be site captains as well

  - You need city staff to ensure volunteers have filled out the necessary forms

- Will pull together volunteer managers

  - Including COH DON, BakerRipley

- Content/Expectations for Volunteer Managers Playbook

  - Interface with the client

  - After-action survey

  - Thanked at the end of the day

  - Is data collection part of this?

    - Recovery efforts require this information, but this information is frequently not shared in a timely manner

  - Once volunteers have signed up for a volunteer experience through an agency, it is the agency’s responsibility to collect data, and people don’t like to share their data

- How can volunteer time data be recorded?

  - Volunteer Houston has features that will be able to track this, but this needs to be set up on the front end

    - This requires volunteers to use Volunteer Houston instead of the agency’s platforms and may cause redundancies in the data collection

    - Each posting would need to have a time associated with it to ensure hours are tracked

    - The benefits need to be clearly communicated to convince agencies to use on common platform (Volunteer Houston)

      - Agencies and partners may not understand why tracking hours is important

    - Once the data is collected, we need to ensure our partners receive the data in a timely manner so they remain engaged in that process

  - Did the check-in, check-out system on Volunteer Houston meet FEMA reimbursement requirements?

  - To loop back: what volunteer hours qualify for reimbursement?

- Agency managers need to be very active to confirm volunteer experiences and responsibilities

# Committee #4 Capacity Building

- Working with civic organizations to be able to take on spontaneous volunteers

- What can we do to build up leadership capacity to be able to train volunteers?

- Problem with the Volunteer Reception Center (VRC) plan requires non-profits to provide staff for these roles

  - In this plan, we would create multiple VRCs

- RUBICON runs VRCs if they are brought in

  - The county has a contract with Interfaith to run the VRC

  - Harvey was the last time a VRC has used